## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Nakshatra | 2025-02-01 | Text extraction error in OCR. | Sprint 1 | Nakshatra | Bug | Applied preprocessing techniques (grayscale, binarization, noise removal). | 2025-02-02 | Open | Needs further investigation.
2 | Nakshatra | 2025-02-05 | Incorrect classification of financial documents. | Sprint 2 | Nakshatra | Model issue | Improved feature extraction & classification model tuning. | 2025-02-07 | Closed | Verified with test cases.
3 | Nakshatra | 2025-02-10 | Low accuracy in extracting tabular data. | Sprint 3 | Nakshatra | Bug | Implemented table structure detection using OpenCV & Pandas. | 2025-02-12 | Open | Further fine-tuning required.
4 | Nakshatra | 2025-02-15 | Bank API data retrieval failed due to restrictions. | Sprint 4 | Nakshatra | API issue | Used an alternative data extraction method & mocked API responses. | 2025-02-16 | Closed | Issue resolved, tested successfully.
5 | Nakshatra | 2025-02-20 | Deployment issues in streamlit environment. | Sprint 5 | Nakshatra | Environment issue | Debugged dependency conflicts and optimized deployment pipeline. | 2025-02-22 | Open | Monitoring for stability.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others